## Read Me
FieldCadence AI — Weekly Flash Report Template
What this is
A one-page weekly operating report for a trade contractor. You fill in one row a week on the Weekly Input tab. The Flash Report tab rebuilds itself from the most recent completed row and compares it to the week before. Nothing else to maintain.
How to use it
1. Open the Weekly Input tab. Row 4 is a filled-in example — type over it or delete it.
2. Add one row per week. Always fill in the Week ending date; the Flash Report finds the latest row by counting dates, so a blank date means that week is ignored.
3. Open the Flash Report tab. Read it before your Monday production meeting, not after.
4. Edit the Targets block at the bottom of the Flash Report so the status flags match how you actually run the business.
Colour legend
Blue text on a yellow fill = a cell you type into.
Black text = calculated. Leave it alone; it will overwrite itself.
The seven numbers this tracks, and why
• Backlog — signed work not yet performed, in dollars and in weeks. Tells you when to hire or stop hiring.
• Work in progress — cost incurred against billed, per the cost-to-cost method. Tells you whether you are financing your customers.
• Gross margin — estimated margin on open work against your target. Tells you what you actually sold.
• Receivables aging — how much is past 60 days and which way it is moving. Tells you who is using you as a bank.
• Crew utilization — billable hours against hours paid. Tells you what you are paying for and not selling.
• Change order capture — approved against issued. Tells you how much work you did for free.
• Cash runway — cash on hand against normal weekly outflow. Tells you how much time you have.
What this does not do
It uses the cost-to-cost method, which assumes your estimate at completion is current. If that number is still the original bid, percent complete is wrong and so is everything downstream — revisit it honestly every month. It does not handle retainage, unapproved change orders, or multi-phase and joint-venture splits. It is not a WIP schedule your bank or bonding company will accept; that needs your accountant and a reconciliation to your general ledger. Use this to find out whether you have a problem. Use your CPA to report it.
Free, no strings
This file is free to use, copy and pass to anyone. It came from FieldCadence AI, part of OwnerCadence AI — weekly operating reports and management oversight for owner-operated businesses. There is an interactive version of the WIP calculation, plus the reasoning behind each of these numbers, at ownercadence.pages.dev/trades — no email required for any of it.

## Weekly Input
WEEKLY INPUT — one row per week. Type over the example in row 4.
Always fill in Week ending — the Flash Report counts dates to find your latest week. Open-jobs columns cover all jobs currently in progress, added together.
Week ending | Signed backlog ($) | Revenue billed this wk | Open jobs: contract $ | Open jobs: est total cost | Open jobs: cost to date | Open jobs: billed to date | AR current | AR 31-60 | AR 61-90 | AR 90+ | Labor hrs paid | Labor hrs billable | Change orders issued $ | Change orders approved $ | Cash on hand | Avg weekly cash out
2026-07-24 | 1431000 | 96500 | 1431000 | 1148500 | 555100 | 607000 | 184000 | 61000 | 28500 | 19000 | 1180 | 902 | 74000 | 51500 | 214000 | 88000

## Flash Report
WEEKLY FLASH REPORT
Week ending |  |  |  | Everything below is calculated.
The Last week and Change columns fill in once Weekly Input has two dated rows.
Metric | This week | Last week | Change | Status
BACKLOG AND WORK IN PROGRESS
Signed backlog
Backlog, weeks of work
Percent complete (cost-to-cost)
Revenue earned to date
BILLING POSITION
Over / (under) billing
Estimated gross margin
RECEIVABLES
Total AR
AR over 60 days
AR over 60 days, share of AR
LABOR AND CHANGE ORDERS
Crew utilization
Unbilled labor hours
Change order capture
Change orders issued, not approved
CASH
Cash on hand
Cash runway, weeks
TARGETS — edit these to match how you run the business
Minimum backlog, weeks | 8
Target gross margin | 20%
Maximum AR over 60 days, share | 15%
Minimum crew utilization | 75%
Minimum change order capture | 90%
Minimum cash runway, weeks | 6
Free from FieldCadence AI · ownercadence.pages.dev/trades · no email required